## Sheet1
2018-04-19
Project |  | CMBS EWS
Owner |  | Ying/Kelven/Shilin
Project Status |  | In Process
Project Objective |  | Develop a framework/Model to predict likelihood of the risk measure, Bloomberg Barclays Investment Grade CMBS Index or its derivative, increase to different warning levels over next 3 months
Background: |  | This project is started at the request of Tokyo HO
Downstream Users |  | CPM, Line of Business
# | Task | Sum Hrs. | Resource Name | 2018-10-12 | 2018-10-19 | 2018-10-26 | 2018-11-02 | 2018-11-09 | 2018-11-16 | 2018-11-23 | 2018-11-30 | 2018-12-07 | 2018-12-14 | 2018-12-21 | 2018-12-28 | 2019-01-04 | 2019-01-11 | 2019-01-18 | 2019-01-25 | Total Person Hours for Task
1 | Project scope | 4 | Ying/Kelven/Emily/CPM | 2018-10-12: 20; 2018-10-19: 20 | 40
2 | Data Collection | 16 | Ying/Kelven/Emily/CPM | 2018-10-12: 40; 2018-10-19: 40; 2018-10-26: 40 | 120
3 | Research Potential Approach | 48 | Ying/Kelven/Emily/CPM | 2018-10-19: 40; 2018-10-26: 40 | 80
4 | Model Development |  |  | 2018-10-19: 40; 2018-10-26: 40; 2018-11-02: 40; 2018-11-09: 40; 2018-11-16: 40; 2018-11-23: 40
5 | Model Review | 80 | Ying/Kelven/Emily/CPM | 2018-11-16: 40; 2018-11-23: 40; 2018-11-30: 40; 2018-12-07: 40; 2018-12-14: 40 | 200
6 | Model Update based on Feedback | 20 | Ying/Kelven/Emily/CPM | 2018-12-07: 40; 2018-12-14: 40; 2018-12-21: 40; 2018-12-28: 40 | 160
7 | Model deck and socialization | 48 | Ying/Kelven/Emily/CPM | 2018-12-28: 20; 2019-01-04: 20; 2019-01-11: 20 | 60
8 | Obtain Model (Conditional) Approval | 16 | Ying/Kelven/Emily/CPM | 2019-01-18: 30; 2019-01-25: 30 | 60
| Total Resources (Person-hours) | 512 |  | 60 | 140 | 120 | 40 | 40 | 80 | 80 | 40 | 80 | 80 | 40 | 60 | 20 | 20 | 30 | 30 | 960
Floating Task
Task to Start
Completed task
Initial approaches proposed
First draft of model form
Fully developed EWS
EWS documentation and package;
Production ready