## Sheet1
2018-04-19
Project |  | CRE EWS
Owner |  | Ying/Kelven/Shilin
Project Status |  | In Process
Project Objective |  | Develop a framework or model to detect the upward trend of the risk measure, Bloomberg Barclays Investment Grade CMBS Index or its derivative as the indicator for CMBS market health. This tool will early warn users the potential increase of market risk levels in next 3 months.
Background: |  | This project is started at the request of Tokyo HO and in collaboration with CPM and business lines.
Downstream Users |  | Line of Business, CPM
# | Task | 2018-10-05 | 2018-10-12 | 2018-10-19 | 2018-10-26 | 2018-11-02 | 2018-11-09 | 2018-11-16 | 2018-11-23 | 2018-11-30 | 2018-12-07 | 2018-12-14 | 2018-12-21 | 2018-12-28 | 2019-01-04 | 2019-01-11 | 2/28/2019 (est.) | Total Person Hours for Task
1 | Project scope | 20 | 20 | [14 empty] | 40
2 | Data Collection | 40 | 40 | 40 | [13 empty] | 120
3 | Research Potential Approaches |  | 40 | 40 | [13 empty] | 80
4 | Model Development |  | 80 | 80 | 80 | 80 | 80 | 80 | [9 empty] | 480
5 | Model Priliminary Review and Refinement | [5 empty] | 80 | 80 | 80 | 80 | 80 | [6 empty] | 400
6 | Model Update based on Feedback | [8 empty] | 40 | 40 | 40 | 40 |  |  |  |  | 160
7 | Model Documentation | [11 empty] | 80 | 80 | 80 |  |  | 240
8 | Obtain Model (Conditional) Approval | [14 empty] | 80 | 200 | 280
| Total Resources (Person-hours) | 60 | 180 | 160 | 80 | 80 | 160 | 160 | 80 | 120 | 120 | 40 | 120 | 80 | 80 | 80 | 200 | 1800
Floating Task
Task to Start
Completed task
Deliverables: Preliminary data analysis and initial approaches proposed
Deliverables: initial selection of models
Deliverables: model fully developed and socialized
Deliverables: EWS documentation and package prepared; available for production
Deliverables: feedbacks and changes on models